## Gantt
Project 1 | Claim your querries by putting it in the description. When your done just set it to 100% | [5 empty] | Legend:
Company Name | I suggest we meet the days with the flag either in person or over skype | [5 empty] | On Track
|  | Project Start Date: |  | 2019-03-07 |  |  | AdventureWorks 2014 |  |  |  |  | DW AdventureWorks |  |  |  |  | Northwinds |  |  | WideWorldImporters |  |  |  |  | DWWideWorldImporters
|  | Display Week: |  | 1 |  |  | March | [27 empty] | April
 | time axis 2019-03-04 to 2019-04-28
[7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | CLAIM DB HERE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Meeting 1: Claim which Table you want to query here first come first serve | Milestone
Querries | On Track | Montes, Alexis | 100% | 2019-03-07 | 5 | AdventureWorks
Querries | On Track | Kopeloff, Jared | 100% | 2019-03-07 | 5 | WideWorldImports
Querries from: | On Track | Narine, Komal | 100% | 2019-03-07 | 5 | DWWideWorldImports
Querries from: | On Track | Bankier Julien | 100% | 2019-03-07 | 5 | NorthWinds
Meeting 2: Querries done/ Plan Presentation/Plan Video | Milestone |  | 100% | 2019-03-10 | 1 | bar: Week 1 S
Review queries, think about what criteria for a good one is | On Track | Montes, Alexis | 100% | 2019-03-10 | 3
Review queries, think about what criteria for a good one is | On Track | Kopeloff, Jared | 100% | 2019-03-10 | 3
Review queries, think about what criteria for a good one is | On Track | Narine, Komal | 100% | 2019-03-10 | 3
Review queries, think about what criteria for a good one is | On Track | Bankier Julien | 100% | 2019-03-10 | 3
Meeting 3: Putting together final project | Milestone |  | 100% | 2019-03-12 | 1 | bar: Week 2 T
Personal slides for pp, personal document, and fixing JB bad quey, and prep for JDBC meeting | On Track | Montes, Alexis | 100% | 2019-03-12 | 4
Personal slides for pp, personal document, and fixing JB bad quey # 2 and prep for JDBC meeting | On Track | Kopeloff, Jared | 100% | 2019-03-12 | 4
Creating the driver for JDBC, Personal slides for pp, personal document, and fixing JB bad quey, and prep for JDBC meeting | On Track | Narine, Komal | 100% | 2019-03-12 | 4
PM acitvites, Setting next meeting, Personal slides for power point, perping for jdbc meeting | On Track | Bankier Julien | 100% | 2019-03-12 | 4
Meeting 4: Final meeting check everything in order | Milestone |  | 100% | 2019-03-15 | 1 | bar: Week 2 F
In charge of splicing video together | On Track | Montes, Alexis | 100% | 2019-03-15 | 1
in charge of final submmisson and proper formatting of submmison | On Track | Kopeloff, Jared | 100% | 2019-03-15 | 1
In charge of JDBC video submmison to google drive | On Track | Narine, Komal | 100% | 2019-03-15 | 1
Set up google drive, in chrage of putting collective PP together | On Track | Bankier Julien | 100% | 2019-03-14 | 1
Final Submisson | Goal |  | 100% | 2019-03-17 | 1 |  | Week 2 S: 2
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.