## Project 1
To-do list
To be completed by: |  | March 17th
Deadline: |  | March 17th
Project 1
% done | Phase | Due By | Notes
100% | Queries | 2019-03-08 | Claim which Table you want to query here first come first serve. There should be 20 in total (Breakdown according to project specs simple (5) to medium (8) to complex (7)). THE QUERIES SHOULD BE FROM ONE OF THESE 5 1. AdventureWorks 2014. 2. Adventure Works DW 2014. 3. Northwinds2019TSQLV5 4. WideWorldImporters. 5 WideWorldImportersDW
100% | Create a SQL file for each of us (x5) | 2019-03-08 | When does it work for you guys to meet and discuss presentaion
100% | Create a voice annotated PowerPoint document | 2019-03-14 | Each in charge of your personal videos
100% | Create jdbc driver | 2019-03-16 | Aaron you’re in charge of this
100% | Create a voice video of the JDBC execution of the group’s three top queries from simple, medium and complex execution. | 2019-03-15 | Meeting over Skype to film the video, I assigned each one of you the queries to fix as we discussed. For the good : I have one, Aaron has one, and Alexis has one. For the bad to be fixed: Alexis you’re fixing mine, Jared you’re fixing my other one ( I marked it in the drive), and I am fixing Aarons
100% | Submit all of the project tracking techniques documentation (plan, to do list, meeting notes, attendance) | 2019-03-16 | I will put it in the drive under the pm tracking folder
100% | Word doc with your diagrams and queries | 2019-03-16 | Each individually doingit
100% | Splice together video | 2019-03-16 | Alexis you’re in charge of this
100% | Final Full Project as VHDX file | 2019-03-16 | Jared you’re in charge of this

## Project 2
To-do list
To be completed by: |  | Name
Deadline: |  | Date
Project 2
% done | Phase | Due By | Notes
0% | Planning
0% | Preparation
0% | Task a
0% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Project 3
To-do list
To be completed by: |  | Name
Deadline: |  | Date
Project 3
% done | Phase | Due By | Notes
0% | Planning
0% | Preparation
0% | Task a
0% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up